## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Green
Project: Chrono
Project Plan
Team Members: Evan Teague ¦ Deylin Nair ¦ Jishen Harilal ¦ Ricardo Yishak Sanchez
Project start date: | 2023-04-24 | Project end date: | 2023-06-05
[5 empty] | April | [6 empty] | May | [34 empty] | June
 | time axis 2023-04-24 to 2023-06-18
Milestone description | Assigned to | Start | End | M | time axis 2023-04-24 to 2023-06-18
UI Development | bar: 2023-04-24 to 2023-05-07
Sign in/log in page | Jishen | 2023-04-24 | 2023-04-30 | bar: 2023-04-24 to 2023-04-30
add timesheet entries | Sanchez | 2023-04-26 | 2023-05-07 | bar: 2023-04-26 to 2023-05-07
add photo option to entries | Deylin | 2023-04-28 | 2023-04-30 | bar: 2023-04-28 to 2023-04-29
add filtering for time entries | JIshen | 2023-04-30 | 2023-05-03 | bar: 2023-04-30 to 2023-05-03
add dark mode option | Evan | 2023-05-02 | 2023-05-05 | bar: 2023-05-02 to 2023-05-05
Firebase Integration | bar: 2023-05-05 to 2023-05-12
firebase user authentication | Sanchez | 2023-05-05 | 2023-05-09 | bar: 2023-05-05 to 2023-05-09
firebase database to store time entries | Jishen | 2023-05-07 | 2023-05-12 | bar: 2023-05-07 to 2023-05-12
Backend Development | bar: 2023-05-09 to 2023-05-20
daily streak system | Jishen | 2023-05-11 | 2023-05-14 | bar: 2023-05-11 to 2023-05-14
reward system | Evan | 2023-05-13 | 2023-05-17 | bar: 2023-05-13 to 2023-05-17
challenges system | Evan | 2023-05-15 | 2023-05-20 | bar: 2023-05-15 to 2023-05-20
notifications + reminders | Sanchez | 2023-05-09 | 2023-05-12 | bar: 2023-05-09 to 2023-05-12
daily goals for user | Deylin | 2023-05-09 | 2023-05-10 | bar: 2023-05-09 to 2023-05-10
Testing | bar: 2023-04-24 to 2023-06-04
Environment | Sanchez | 2023-05-25 | 2023-05-29 | bar: 2023-05-25 to 2023-05-29
System test | Sanchez | 2023-05-27 | 2023-06-01 | bar: 2023-05-27 to 2023-06-01
Issues/bugs | Evan | 2023-04-24 | 2023-06-04 | bar: 2023-04-24 to 2023-06-04

## Blue
Project: Blue
Contoso, Ltd.
Gurpreet Bawa
Project start date: | 2023-04-21 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | May | [27 empty] | June
 | time axis 2023-05-04 to 2023-06-28
Milestone description | Assigned to | Progress | Start | Days | time axis 2023-05-04 to 2023-06-28
Title 1
Task 1 |  | 25% | 2023-04-24 | 3
Task 2 |  |  | 2023-04-29 | 1
Task 3 |  | 50% | 2023-04-21 | 10
Task 4 |  |  | 2023-05-14 | 1 | bar: 2023-05-14
Task 5 |  | 10% | 2023-04-30 | 6
Title 2
Task 1 |  | 60% | 2023-04-30 | 13
Task 2 |  | 50% | 2023-05-01 | 9
Task 3 |  | 33% | 2023-05-09 | 11
Task 4 |  |  | 2023-05-18 | 1 | bar: 2023-05-18
Task 5 |  |  | 2023-05-19 | 24
Title 3
Task 1 |  |  | 2023-05-09 | 4
Task 2 |  |  | 2023-05-13 | 14
Task 3 |  |  | 2023-05-29 | 6
Task 4 |  |  | 2023-06-11 | 3
Task 5 |  |  | 2023-06-03 | 19
Title 4
Task 1 |  |  | 2023-05-31 | 15
Task 2 |  |  | 2023-05-23 | 5
Task 3 |  |  | 2023-07-13 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Purple
Project: Purple
Contoso, Ltd.
Hayden Cook
Project start date: | 2023-04-21 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | May | [27 empty] | June
 | time axis 2023-05-04 to 2023-06-28
Milestone description | Assigned to | Progress | Start | Days | time axis 2023-05-04 to 2023-06-28
Title 1
Task 1 |  | 25% | 2023-04-24 | 3
Task 2 |  |  | 2023-04-29 | 1
Task 3 |  | 50% | 2023-04-21 | 10
Task 4 |  |  | 2023-05-14 | 1 | bar: 2023-05-14
Task 5 |  | 10% | 2023-04-30 | 6
Title 2
Task 1 |  | 60% | 2023-04-30 | 13
Task 2 |  | 50% | 2023-05-01 | 9
Task 3 |  | 33% | 2023-05-09 | 11
Task 4 |  |  | 2023-05-18 | 1 | bar: 2023-05-18
Task 5 |  |  | 2023-05-19 | 24
Title 3
Task 1 |  |  | 2023-05-09 | 4
Task 2 |  |  | 2023-05-13 | 14
Task 3 |  |  | 2023-05-29 | 6
Task 4 |  |  | 2023-06-11 | 3
Task 5 |  |  | 2023-06-03 | 19
Title 4
Task 1 |  |  | 2023-05-31 | 15
Task 2 |  |  | 2023-05-23 | 5
Task 3 |  |  | 2023-07-13 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one